| Areas of Work | What actions | Who to do | By When | Progress update /Complete |
| --- | --- | --- | --- | --- |
| Governance | Review and update Memorandum of Agreement Invite new members to join the group from Voluntary sector orgs. Consider induction prog Formalise the relationship with sub groups. Agree and record a remit with sub groups and ask for regular updates, and info on stats, evaluation etc to be recorded. Induction with sub groups as required so they are fully aware of the origins of their work and the full context. Invite Practitioners to join groups Re-establish a Community Empowerment group Administer and report on CLDSC grant Explore potential links with RIC(s) | All All Who to progress? Administer through Fife Council. RM/others | June 2019 Sept 2019 Dec 2019 March 2020 Ongoing at present | Memo updated May 27th 2019 Rep from Dundee TSI has left. New postholder to be invited to join. New rep from Volunteer Dundee nominated. ESOL Practitioners network has Terms of Reference doc agreed. This can be template for other sub groups CLDSC have given commitment to funding for 2019-20 New link with Education Scotland (Susan Epsworth) established |
| Planning | Use findings from our research project to inform planning. Youth Work core training Explore needs, plan prog, SQA development and delivery. Explore possible joint work on this. Digital skills. Explore needs and resources available including sharing the skills within the workforce Map all Partnership learning opps to relevant Competences (and Ethics if appropriate), and highlight this in publicity Identify the number of learning hours in each learning opportunity. Produce newsletter for 2019 Peer Review exercise using Self Evaluation toolkit across Alliance partners | All GB/PG/TR SHS/ TR/VW SHS/ who else? All SHS lead/all contributing All with support from Education Scotland (SE) | Dec 2019 Dec 2019 Sept 2019 Dec 2019 Ongoing Aug 2019 June 2020 | Development session held on 22.10.18, follow up on 28th Jan. Fife offering T4T opps on Principles and Practice of youth Work Working group met in March. Planning underway for Intro to Assessment workshop. Joint work on AAA is happening 4 Places paid for last year on course. Lots of digital skills online learning resources available too We have been awarded CLDSC Standards Mark so we are required to map to Competences and number of hours CPD. We need to ensure this happens for every learning opp. Group space is open to all. Materials uploaded after events. (this is condition of grant) Proposed process outline created by working group |
| Delivery | Family Learning Conference Youth Work training prog CLD Ethics HIIC training for trainers Peer Evaluation exercise Volunteer management? | FL sub group YW sub group SHS/TR VW/SHS All GB | 30th Oct 2019 June 2020 Sept 2019 Sept 2019 June 2020 ? | Planning well underway. Venue Bertha Park Perth First session delivered in May. Second planned for Sept. T4T model started Training was delivered in April. 16 people attended including 2 volunteers Small scale volunteer core training prog has been trialled in Dundee. Volunteer Dundee will be partner in this going forward |
| Review | Create standardised templates for booking places on events; feedback from participants. Locate on i-develop Hold review/debrief sessions after each learning opp with all organisers and record improvement actions centrally on i-develop. Do annual self-evaluation exercise using selected Qis/challenge questions from HGIOLDOC framework Complete annual work/improvement plan | Who to lead on this? All Who to lead? (with support from AAs) | Dec 2019 ongoing autumn 2019 | Logo now created, and banners available for our events Review sessions have been held after events e.g. Family Learning conference First self-evaluation exercise was carried out spring 2018 Workplan created and updated for 2019 |